## Sheet1
Rig Type | Rig Name | Well Name | Activity Type | Activity Description | Start Date | End Date | Year - Start | Year - End | Duration
MODU | Condor | DEEP MENSA | ABANDONMENT | Mensa | 2014-07-10 | 2014-11-04 | 2014 | 2014 | 117
MODU | Condor | MENSA A2 | ABANDONMENT | Mensa | 2014-11-04 | 2014-11-21 | 2014 | 2014 | 17
MODU | Condor | MENSA A3 | ABANDONMENT | Mensa | 2014-11-21 | 2014-12-07 | 2014 | 2014 | 16
MODU | Condor | MENSA A1 | ABANDONMENT | Mensa | 2014-12-07 | 2015-01-19 | 2014 | 2015 | 43
MODU | Condor | MENSA A5 | ABANDONMENT | Mensa | 2015-01-19 | 2015-03-11 | 2015 | 2015 | 51
MODU | Condor | MENSA A6 | ABANDONMENT | Mensa | 2015-03-11 | 2015-03-31 | 2015 | 2015 | 20
MODU | Condor | CONDOR IDLE | RIG - IDLE | Idle | 2015-03-31 | 2015-11-07 | 2015 | 2015 | 221
MODU | Condor | GREAT WHITE GB006 | WHOLE DRILLING EVENT | Perdido GB006_I | 2015-11-07 | 2016-01-21 | 2015 | 2016 | 75
MODU | Condor | GREAT WHITE GB006 | WHOLE COMPLETION EVENT |  | 2016-01-21 | 2016-03-03 | 2016 | 2016 | 42
MODU | Condor | CONDOR IDLE | RIG - IDLE | Idle | 2016-03-03 | 2016-05-02 | 2016 | 2016 | 60
MODU | Condor | MACARONI A2 | ABANDONMENT | Mac Field PA | 2016-05-02 | 2016-07-12 | 2016 | 2016 | 71
MODU | Condor | MACARONI A4 | ABANDONMENT | Mac Field PA | 2016-07-12 | 2016-08-20 | 2016 | 2016 | 39
MODU | Condor | MACARONI A5 | ABANDONMENT | Mac Field PA | 2016-08-20 | 2016-09-28 | 2016 | 2016 | 39
MODU | Condor | MACARONI EXPL | ABANDONMENT | Mac Field PA | 2016-09-28 | 2016-11-19 | 2016 | 2016 | 52
MODU | Noble Don Taylor | PRINCESS P8 | WHOLE DRILLING EVENT | Princess P8 (formally P5 ST) | 2015-01-18 | 2015-06-11 | 2015 | 2015 | 144
MODU | Noble Don Taylor | PRINCESS P8 | WHOLE COMPLETION EVENT |  | 2015-06-11 | 2015-07-24 | 2015 | 2015 | 43
MODU | Noble Don Taylor | URSA UI4 | DRILLING - PILOT HOLE | UI-2ST (Formally Ursa UI 4 New Well) | 2015-07-24 | 2015-11-03 | 2015 | 2015 | 102
MODU | Noble Don Taylor | URSA UI4 | WHOLE DRILLING EVENT |  | 2015-11-03 | 2015-12-04 | 2015 | 2015 | 31
MODU | Noble Don Taylor | URSA UI4 | WHOLE COMPLETION EVENT |  | 2015-12-04 | 2016-01-13 | 2015 | 2016 | 40
MODU | Noble Don Taylor | PRINCESS P7 ST1 | WHOLE DRILLING EVENT | Princess P7 SHST (Formally UHRC) | 2016-01-13 | 2016-03-14 | 2016 | 2016 | 61
MODU | Noble Don Taylor | PRINCESS P7 ST1 | WHOLE COMPLETION EVENT |  | 2016-03-14 | 2016-05-05 | 2016 | 2016 | 52
MODU | Noble Don Taylor | URSA UI3 | DRILLING - PILOT HOLE | Ursa UI 4 New Well (formally UI-3) | 2016-05-05 | 2016-09-20 | 2016 | 2016 | 138
MODU | Noble Don Taylor | URSA UI3 | WHOLE DRILLING EVENT |  | 2016-09-20 | 2016-10-31 | 2016 | 2016 | 41
MODU | Noble Don Taylor | URSA UI3 | WHOLE COMPLETION EVENT |  | 2016-10-31 | 2016-12-27 | 2016 | 2016 | 57
MODU | Noble Don Taylor | STONES 7 RE-DRILL | WHOLE DRILLING EVENT | Stones 7 Redrill D&C | 2016-12-27 | 2017-06-14 | 2016 | 2017 | 169
MODU | Noble Don Taylor | STONES 7 RE-DRILL | WHOLE COMPLETION EVENT |  | 2017-06-14 | 2017-09-24 | 2017 | 2017 | 102
MODU | Noble Don Taylor | STONES 8 | WHOLE DRILLING EVENT | Stones 8 D&C | 2017-09-24 | 2018-03-04 | 2017 | 2018 | 161
MODU | Noble Don Taylor | STONES 8 | WHOLE COMPLETION EVENT |  | 2018-03-04 | 2018-06-07 | 2018 | 2018 | 95
MODU | Noble Don Taylor | STONES 10 | WHOLE DRILLING EVENT | Stones 10 D&C | 2018-06-07 | 2018-11-18 | 2018 | 2018 | 164
MODU | Noble Don Taylor | STONES 10 | WHOLE COMPLETION EVENT |  | 2018-11-18 | 2019-02-13 | 2018 | 2019 | 87
MODU | Noble Don Taylor | APPO WEST | WHOLE DRILLING EVENT | Appo West | 2019-02-13 | 2019-06-26 | 2019 | 2019 | 133
MODU | Noble Don Taylor | APPO PS7 | WHOLE COMPLETION EVENT | Well AC006 (PS7) | 2019-06-26 | 2019-09-10 | 2019 | 2019 | 76
MODU | Noble Don Taylor | APPO PS9 | WHOLE COMPLETION EVENT | Well AE006 (PS9) | 2019-09-10 | 2019-11-13 | 2019 | 2019 | 64
MODU | Noble Don Taylor | APPO PNE2 | WHOLE COMPLETION EVENT | Well AE001 (PNE2) | 2019-11-13 | 2020-01-22 | 2019 | 2020 | 70
MODU | Noble Don Taylor | APPO PC1 | WHOLE DRILLING EVENT | Well AC005 (PC1) | 2020-01-22 | 2020-06-04 | 2020 | 2020 | 134
MODU | Noble Don Taylor | APPO PC1 | WHOLE COMPLETION EVENT |  | 2020-06-04 | 2020-07-18 | 2020 | 2020 | 44
MODU | Noble Don Taylor | APPO PV3 | WHOLE DRILLING EVENT | Well VX006 (PV3) | 2020-07-18 | 2020-11-24 | 2020 | 2020 | 129
MODU | Noble Don Taylor | APPO PV3 | WHOLE COMPLETION EVENT |  | 2020-11-24 | 2021-01-03 | 2020 | 2021 | 40
MODU | Noble Don Taylor | APPO PS11 | WHOLE DRILLING EVENT | Well AE005 (PS11) | 2021-01-03 | 2021-05-01 | 2021 | 2021 | 118
MODU | Noble Don Taylor | APPO PS11 | WHOLE COMPLETION EVENT |  | 2021-05-01 | 2021-06-14 | 2021 | 2021 | 44
MODU | Nautilus | GLIDER 7 | WHOLE DRILLING EVENT | Glider 7 Drill and Complete | 2014-02-19 | 2014-10-06 | 2014 | 2014 | 229
MODU | Nautilus | GLIDER 7 | WHOLE COMPLETION EVENT |  | 2014-10-06 | 2015-02-18 | 2014 | 2015 | 135
MODU | Nautilus | GLIDER 8 | WHOLE COMPLETION EVENT | Glider 8 Complete | 2015-02-18 | 2015-04-23 | 2015 | 2015 | 64
MODU | Nautilus | NAUTILUS RIG UPGRADE | n/a | Rig Upgrade | 2015-04-23 | 2015-08-21 | 2015 | 2015 | 120
MODU | Nautilus | COULOMB | WHOLE DRILLING EVENT | Coulomb | 2015-08-21 | 2015-12-13 | 2015 | 2015 | 114
MODU | Nautilus | COULOMB | WHOLE COMPLETION EVENT |  | 2015-12-13 | 2016-01-23 | 2015 | 2016 | 41
MODU | Nautilus | NAUTILUS RIG IDLE | RIG - IDLE | Idle | 2016-01-23 | 2016-05-21 | 2016 | 2016 | 119
MODU | Nautilus | POPEYE PA | ABANDONMENT | Popeye PA | 2016-05-21 | 2016-10-28 | 2016 | 2016 | 160
MODU | Nautilus | NAUTILUS RIG IDLE | RIG - IDLE | Idle | 2016-10-28 | 2017-08-18 | 2016 | 2017 | 294
MODU | Nautilus | TROIKA PA | ABANDONMENT | Troika TA's | 2017-06-19 | 2017-08-18 | 2017 | 2017 | 60
MODU | Bully 1 | WEST BOREAS WB002 | WHOLE DRILLING EVENT | WB002 D&C | 2014-08-23 | 2015-01-17 | 2014 | 2015 | 147
MODU | Bully 1 | WEST BOREAS WB002 | WHOLE COMPLETION EVENT |  | 2015-01-17 | 2015-03-15 | 2017 | 2020 | 57
MODU | Bully 1 | SOUTH DEIMOS 2 | WHOLE DRILLING EVENT | SD2 D&C | 2015-03-15 | 2015-08-25 | 2015 | 2015 | 163
MODU | Bully 1 | SOUTH DEIMOS 2 | WHOLE COMPLETION EVENT |  | 2015-08-25 | 2015-11-05 | 2015 | 2015 | 72
MODU | Bully 1 | BULLY 1 IDLE | RIG - IDLE | Idle | 2015-11-05 | 2016-01-01 | 2015 | 2016 | 57
MODU | Bully 1 | BULLY 1 DRY DOCK | n/a | Bully One Dry Dock & BOP COC | 2016-01-01 | 2016-02-15 | 2016 | 2016 | 45
MODU | Bully 1 | BULLY 1 IDLE | RIG - IDLE | Idle | 2016-02-15 | 2017-03-19 | 2016 | 2017 | 398
MODU | Bully 1 | DEIMOS PA | ABANDONMENT | Deimos PA's (DM002 and DM003) | 2016-02-15 | 2016-06-14 | 2016 | 2016 | 120
MODU | Noble Globetrotter 1 | KAIKIAS ST | WHOLE DRILLING EVENT | Kaikias #2/Kaikias #3 | 2014-12-28 | 2015-07-01 | 2014 | 2015 | 185
MODU | Noble Globetrotter 1 | MERCURY | WHOLE DRILLING EVENT | Mercury | 2015-07-01 | 2016-01-13 | 2015 | 2016 | 196
MODU | Noble Globetrotter 1 | FORT SUMTER | WHOLE DRILLING EVENT | Fort Sumter | 2016-01-13 | 2016-06-10 | 2016 | 2016 | 149
MODU | Noble Globetrotter 1 | WHALE | WHOLE DRILLING EVENT | Whale | 2016-06-10 | 2016-10-01 | 2016 | 2016 | 113
MODU | Noble Globetrotter 1 | LEESBURG | WHOLE DRILLING EVENT | Leesburg | 2016-10-01 | 2017-02-10 | 2016 | 2017 | 132
MODU | Noble Globetrotter 1 | NOZOMI | WHOLE DRILLING EVENT | Nozomi | 2017-02-10 | 2017-06-08 | 2017 | 2017 | 118
MODU | Noble Globetrotter 1 | BULL RUN | WHOLE DRILLING EVENT | Bull Run | 2017-06-08 | 2017-10-31 | 2017 | 2017 | 145
MODU | Noble Globetrotter 1 | CORAZON | WHOLE DRILLING EVENT | Corazon | 2017-10-31 | 2018-03-24 | 2017 | 2018 | 144
MODU | Noble Globetrotter 1 | UAD PA | ABANDONMENT | UAD P&A Placeholder | 2018-03-24 | 2018-05-18 | 2018 | 2018 | 55
MODU | Noble Globetrotter 1 | FOURIER DP | WHOLE DRILLING EVENT | Fourier Dp | 2018-05-18 | 2018-10-10 | 2018 | 2018 | 145
MODU | Noble Globetrotter 1 | PA | ABANDONMENT | P&A Placeholder | 2018-10-10 | 2018-12-04 | 2018 | 2018 | 55
MODU | Noble Globetrotter 1 | DAYLIGHT | WHOLE DRILLING EVENT | Daylight | 2018-12-04 | 2019-04-28 | 2018 | 2019 | 145
MODU | Noble Globetrotter 1 | KIRK | WHOLE DRILLING EVENT | Kirk | 2019-04-28 | 2019-09-20 | 2019 | 2019 | 145
MODU | Noble Globetrotter 1 | DUCIE ISLAND | WHOLE DRILLING EVENT | Ducie Island | 2019-09-20 | 2020-02-12 | 2019 | 2020 | 145
MODU | Noble Globetrotter 1 | STONEWALL | WHOLE DRILLING EVENT | Stonewall | 2020-02-12 | 2020-07-06 | 2020 | 2020 | 145
MODU | Noble Jim Day | STONES 5 RE-DRILL | WHOLE DRILLING EVENT | Stones 5 Redrill Drill | 2014-08-02 | 2015-03-15 | 2014 | 2015 | 225
MODU | Noble Jim Day | STONES 9 | WHOLE DRILLING EVENT | Stones 9 Drill | 2015-03-15 | 2015-08-14 | 2015 | 2015 | 152
MODU | Noble Jim Day | STONES SUBSEA INSTALL WINDOW | PROJECTS - SUBSEA INSTALLATION | Stones Subsea Install Window | 2015-08-14 | 2015-09-28 | 2015 | 2015 | 45
MODU | Noble Jim Day | STONES 9 | WHOLE COMPLETION EVENT | Stones 9 Complete | 2015-09-28 | 2015-12-25 | 2015 | 2015 | 88
MODU | Noble Jim Day | STONES 5 RE-DRILL | WHOLE COMPLETION EVENT | Stones 5 Complete | 2015-12-25 | 2016-04-05 | 2015 | 2016 | 102
MODU | Ice Max | POWER NAP | WHOLE DRILLING EVENT | Power Nap | 2014-08-21 | 2014-12-17 | 2014 | 2014 | 119
MODU | Ice Max | POWER NAP SCL | LOGGING |  | 2014-12-17 | 2015-01-11 | 2014 | 2015 | 25
MODU | Ice Max | POWER NAP ST | WHOLE DRILLING EVENT |  | 2015-01-11 | 2015-03-06 | 2015 | 2015 | 54
MODU | Ice Max | POWER NAP ST2 | WHOLE DRILLING EVENT |  | 2015-03-06 | 2015-04-06 | 2015 | 2015 | 31
MODU | Ice Max | DEEP SLEEP | WHOLE DRILLING EVENT | Deep Sleep | 2015-04-06 | 2015-10-11 | 2015 | 2015 | 188
MODU | Ice Max | ICE MAX MOB TO NS | RIG - MOBILISATION | Mob | 2015-10-11 | 2015-11-21 | 2015 | 2015 | 41
MODU | Ice Max | NOVA SCOTIA 1 | WHOLE DRILLING EVENT | Nova Scotia 1 | 2015-11-21 | 2016-04-19 | 2015 | 2016 | 150
MODU | Ice Max | NOVA SCOTIA 2 | WHOLE DRILLING EVENT | Nova Scotia 2 | 2016-04-19 | 2016-09-17 | 2016 | 2016 | 151
MODU | Ice Max | ICE MAX MOB TO GOM | RIG - MOBILISATION | Mob | 2016-09-17 | 2016-10-28 | 2016 | 2016 | 41
MODU | Ice Max | ARBUCKLE | WHOLE DRILLING EVENT | Arbuckle | 2016-10-28 | 2017-04-02 | 2016 | 2017 | 156
MODU | Ice Max | YAKIMA | WHOLE DRILLING EVENT | Ipanema | 2017-04-02 | 2017-10-13 | 2017 | 2017 | 194
MODU | Thalassa | STONES 6 | WHOLE DRILLING EVENT | Stones 6 | 2015-12-31 | 2016-06-22 | 2015 | 2016 | 174
MODU | Thalassa | STONES 6 | WHOLE COMPLETION EVENT |  | 2016-06-22 | 2016-10-11 | 2016 | 2016 | 111
MODU | Thalassa | SILVERTIP SA004 | WHOLE DRILLING EVENT | Silvertip SA004 | 2016-10-11 | 2016-11-30 | 2016 | 2016 | 50
MODU | Thalassa | SILVERTIP SA004 | WHOLE COMPLETION EVENT |  | 2016-11-30 | 2017-01-01 | 2016 | 2017 | 32
MODU | Thalassa | VITO BATCH B | DRL - TOP HOLE ONLY | Vito Batch B | 2017-01-01 | 2017-05-07 | 2017 | 2017 | 126
MODU | Thalassa | VITO BATCH A | DRL - TOP HOLE ONLY | Vito Batch A | 2017-05-07 | 2017-09-10 | 2017 | 2017 | 126
MODU | Thalassa | VITO 7 | WHOLE DRILLING EVENT | Vito P7 | 2017-09-10 | 2018-02-06 | 2017 | 2018 | 149
MODU | Thalassa | VITO 7 | WHOLE COMPLETION EVENT |  | 2018-02-06 | 2018-03-17 | 2018 | 2018 | 39
MODU | Thalassa | VITO 6 | WHOLE DRILLING EVENT | Vito P6 | 2018-03-17 | 2018-08-09 | 2018 | 2018 | 145
MODU | Thalassa | VITO 6 | WHOLE COMPLETION EVENT |  | 2018-08-09 | 2018-09-13 | 2018 | 2018 | 35
MODU | Thalassa | VITO 8 | WHOLE DRILLING EVENT | Vito P8 | 2018-09-13 | 2019-01-15 | 2018 | 2019 | 124
MODU | Thalassa | VITO 8 | WHOLE COMPLETION EVENT |  | 2019-01-15 | 2019-02-17 | 2019 | 2019 | 33
MODU | Thalassa | VITO 5 | WHOLE DRILLING EVENT | Vito P5 | 2019-02-17 | 2019-06-26 | 2019 | 2019 | 129
MODU | Thalassa | VITO 5 | WHOLE COMPLETION EVENT |  | 2019-06-26 | 2019-07-28 | 2019 | 2019 | 32
MODU | Thalassa | VITO 4 | WHOLE DRILLING EVENT | Vito P4 | 2019-07-28 | 2019-12-02 | 2019 | 2019 | 127
MODU | Thalassa | VITO 4 | WHOLE COMPLETION EVENT |  | 2019-12-02 | 2020-01-02 | 2019 | 2020 | 31
MODU | Proteus | APPO PS2 | WHOLE DRILLING EVENT | Pre-drill well AW006 (PS2) | 2016-06-16 | 2016-10-27 | 2016 | 2016 | 133
MODU | Proteus | APPO PS4 | WHOLE DRILLING EVENT | Pre-drill well AW001 (PS4) - includes pilot hole | 2016-10-27 | 2017-03-16 | 2016 | 2017 | 140
MODU | Proteus | APPO PNE2 | WHOLE DRILLING EVENT | Pre-drill well AE001 (PNE2) - includes pilot hole | 2017-03-16 | 2017-07-13 | 2017 | 2017 | 119
MODU | Proteus | APPO PS9 | WHOLE DRILLING EVENT | Pre-drill well AE006 (PS9) | 2017-07-13 | 2017-10-29 | 2017 | 2017 | 108
MODU | Proteus | APPO PS7 | WHOLE DRILLING EVENT | Pre-drill well AC006 (PS7) | 2017-10-29 | 2018-02-12 | 2017 | 2018 | 106
MODU | Proteus | APPO PV1 | WHOLE DRILLING EVENT | Pre-drill well VX002 (PV1) | 2018-02-12 | 2018-05-27 | 2018 | 2018 | 104
MODU | Proteus | PROTEUS IDLE | RIG - IDLE | Idle | 2018-05-27 | 2018-12-17 | 2018 | 2018 | 204
MODU | Proteus | APPO PS4 | WHOLE COMPLETION EVENT | Well AW001 (PS4) | 2018-12-17 | 2019-03-01 | 2018 | 2019 | 74
MODU | Proteus | APPO PS2 | WHOLE COMPLETION EVENT | Well AW006 (PS2) | 2019-03-01 | 2019-05-12 | 2019 | 2019 | 72
MODU | Proteus | APPO PV1 | WHOLE COMPLETION EVENT | Well VX002 (PV1) | 2019-05-12 | 2019-07-17 | 2019 | 2019 | 66
MODU | Proteus | APPO IS3 | WHOLE DRILLING EVENT | Well IW003 (IS3) | 2019-07-17 | 2019-12-01 | 2019 | 2019 | 137
MODU | Proteus | APPO IS3 | WHOLE COMPLETION EVENT |  | 2019-12-01 | 2020-01-15 | 2019 | 2019 | 45
MODU | Proteus | APPO IS5 | WHOLE DRILLING EVENT | Well IE003 (IS5) | 2020-01-15 | 2020-05-17 | 2020 | 2020 | 123
MODU | Proteus | APPO IS5 | WHOLE COMPLETION EVENT |  | 2020-05-17 | 2020-07-03 | 2019 | 2019 | 47
MODU | Pontus | GREAT WHITE GD002 | WHOLE DRILLING EVENT | GW Frio GD002_P | 2016-12-31 | 2017-03-05 | 2016 | 2017 | 64
MODU | Pontus | GREAT WHITE GD002 | WHOLE COMPLETION EVENT |  | 2017-03-05 | 2017-04-01 | 2019 | 2020 | 27
MODU | Pontus | GREAT WHITE GD003 | WHOLE DRILLING EVENT | GW Frio GD003_P | 2017-04-01 | 2017-06-04 | 2017 | 2017 | 64
MODU | Pontus | GREAT WHITE GD003 | WHOLE COMPLETION EVENT |  | 2017-06-04 | 2017-07-01 | 2020 | 2020 | 27
MODU | Pontus | CARAMEL KEG | WHOLE DRILLING EVENT | Caramel Keg | 2017-07-01 | 2018-01-18 | 2017 | 2018 | 201
MODU | Pontus | SHADOW | WHOLE DRILLING EVENT | Shadow | 2018-01-18 | 2018-06-06 | 2018 | 2018 | 139
MODU | Pontus | STONEYKIRK | WHOLE DRILLING EVENT | Stoneykirk | 2018-06-06 | 2018-12-14 | 2018 | 2018 | 191
MODU | Pontus | LIVE OAK | WHOLE DRILLING EVENT | Live Oak | 2018-12-14 | 2019-03-25 | 2018 | 2019 | 101
MODU | Pontus | MIOCENE (NFE/NIE) | WHOLE DRILLING EVENT | Miocene (NFE/NIE) | 2019-03-25 | 2019-08-02 | 2019 | 2019 | 130
MODU | Pontus | STONES 11 | WHOLE DRILLING EVENT | Stones 11 D&C | 2019-08-02 | 2019-12-22 | 2019 | 2019 | 142
MODU | Pontus | STONES 11 | WHOLE COMPLETION EVENT |  | 2019-12-22 | 2020-03-18 | 2016 | 2016 | 87
MODU | Pontus | STONES 12 | WHOLE DRILLING EVENT | Stones 12 D&C | 2020-03-18 | 2020-08-10 | 2020 | 2020 | 145
MODU | Pontus | STONES 12 | WHOLE COMPLETION EVENT |  | 2020-08-10 | 2020-11-08 | 2016 | 2016 | 90
MODU | Pontus | BIG BROWN | WHOLE DRILLING EVENT | Big Brown | 2020-11-08 | 2021-03-27 | 2020 | 2021 | 139
MODU | Pontus | ARANSAS | WHOLE DRILLING EVENT | Aransas | 2021-03-27 | 2021-09-23 | 2021 | 2021 | 180
MODU | Poseidon | POSEIDON IDLE | RIG - IDLE | Idle | 2017-05-02 | 2018-05-02 | 2017 | 2018 | 365
MODU | Poseidon | VITO 12 | WHOLE DRILLING EVENT | Vito PROD12 D&C | 2018-05-02 | 2018-10-07 19:12 | 2018 | 2018 | 158.8
MODU | Poseidon | VITO 12 | WHOLE COMPLETION EVENT |  | 2018-10-07 19:12 | 2018-11-18 02:24 | 2018 | 2018 | 41.3
MODU | Poseidon | VITO 3 | WHOLE DRILLING EVENT | Vito PROD3 D&C | 2018-11-18 02:24 | 2019-04-20 | 2018 | 2019 | 152.9
MODU | Poseidon | VITO 3 | WHOLE COMPLETION EVENT |  | 2019-04-20 | 2019-05-25 07:12 | 2019 | 2019 | 35.3
MODU | Poseidon | VITO 9 | WHOLE DRILLING EVENT | Vito PROD9 D&C | 2019-05-25 07:12 | 2019-09-24 12:00 | 2019 | 2019 | 122.2
MODU | Poseidon | VITO 9 | WHOLE COMPLETION EVENT |  | 2019-09-24 12:00 | 2019-10-27 12:00 | 2019 | 2019 | 33
MODU | Poseidon | VITO 2 | WHOLE DRILLING EVENT | Vito PROD2 D&C | 2019-10-27 12:00 | 2020-03-06 19:12 | 2019 | 2020 | 131.3
MODU | Poseidon | VITO 2 | WHOLE COMPLETION EVENT |  | 2020-03-06 19:12 | 2020-04-07 09:36 | 2020 | 2020 | 31.6
MODU | Poseidon | VITO 12 | WHOLE DRILLING EVENT | Vito PROD1 D&C | 2020-04-07 09:36 | 2020-09-04 | 2020 | 2020 | 149.6
MODU | Poseidon | VITO 12 | WHOLE COMPLETION EVENT |  | 2020-09-04 | 2020-10-04 16:48 | 2020 | 2020 | 30.7
MODU | Poseidon | VITO 10 | WHOLE DRILLING EVENT | Vito PROD10 D&C | 2020-10-04 16:48 | 2021-01-25 09:36 | 2020 | 2021 | 112.7
MODU | Poseidon | VITO 10 | WHOLE COMPLETION EVENT |  | 2021-01-25 09:36 | 2021-02-24 14:24 | 2021 | 2021 | 30.2
MODU | Poseidon | VITO 2 Inj | WHOLE DRILLING EVENT | Vito INJ2 D&C | 2021-02-24 14:24 | 2021-07-04 02:24 | 2021 | 2021 | 129.5
MODU | Poseidon | VITO 2 Inj | WHOLE COMPLETION EVENT |  | 2021-07-04 02:24 | 2021-08-09 19:12 | 2021 | 2021 | 36.7
MODU | Poseidon | VITO 3 Inj | WHOLE DRILLING EVENT | Vito INJ3 D&C | 2021-08-09 19:12 | 2021-12-19 12:00 | 2021 | 2021 | 131.7
MODU | Poseidon | VITO 3 Inj | WHOLE COMPLETION EVENT |  | 2021-12-19 12:00 | 2022-01-25 04:48 | 2021 | 2022 | 36.7
DVA | Perdido | GREAT WHITE GA006 | WHOLE DRILLING EVENT | GA006_I D&C | 2015-01-11 | 2015-05-13 | 2015 | 2015 | 122
DVA | Perdido | GREAT WHITE GA006 | WHOLE COMPLETION EVENT |  | 2015-05-13 | 2015-06-12 | 2015 | 2015 | 30
DVA | Perdido | PERDIDO IDLE - WARM STACK (4032) | RIG - IDLE | Warm Stack Down Time | 2015-06-12 | 2015-12-09 | 2015 | 2015 | 180
DVA | Perdido | PERDIDO SBS 2015 | RIG - MAINTENAINCE | SBS 2015 | 2015-12-09 | 2016-01-14 | 2015 | 2016 | 36
DVA | Perdido | PERDIDO WORKOVER/INTERVENTION 2015 | WORKOVER | Workover / Intervention 2015 | 2016-01-14 | 2016-02-04 | 2016 | 2016 | 21
DVA | Perdido | PERDIDO ARM 2015 | RIG - MAINTENAINCE | ARM 2015 | 2016-02-04 | 2016-02-18 | 2016 | 2016 | 14
DVA | Perdido | GREAT WHITE GA018 | COM - DE-COMPLETION | GA018 Slot Recovery | 2016-02-18 | 2016-03-22 | 2016 | 2016 | 33
DVA | Perdido | GREAT WHITE GA018 | WHOLE DRILLING EVENT | GA018_ST_P D&C | 2016-03-22 | 2016-06-08 | 2016 | 2016 | 78
DVA | Perdido | GREAT WHITE GA018 | WHOLE COMPLETION EVENT |  | 2016-06-08 | 2016-08-02 | 2020 | 2020 | 55
DVA | Perdido | PERDIDO SBS 2016 | RIG - MAINTENAINCE | SBS 2016 | 2016-08-02 | 2016-08-22 | 2016 | 2016 | 20
DVA | Perdido | PERDIDO WORKOVER/INTERVENTION 2016 | WORKOVER | Workover / Intervention 2016 | 2016-08-22 | 2016-09-12 | 2016 | 2016 | 21
DVA | Perdido | PERDIDO ARM 2016 | RIG - MAINTENAINCE | ARM 2016 | 2016-09-12 | 2016-09-24 | 2016 | 2016 | 12
DVA | Perdido | PERDIDO MAJOR INTEGRITY SHUTDOWN 2016 | RIG - IDLE | MIS (Major Integrity Shutdown) 2016 | 2016-09-24 | 2016-09-29 | 2016 | 2016 | 5
DVA | Perdido | PERDIDO D&C RISER DOWNTIME 2016 | RIG - RISER MAINTENANCE (TLP/SPAR) | D&C Riser Downtime 2016 | 2016-09-29 | 2016-10-29 | 2016 | 2016 | 30
DVA | Perdido | GREAT WHITE GA022 | WHOLE DRILLING EVENT | GA022_I D&C | 2016-10-29 | 2017-01-21 | 2016 | 2017 | 84
DVA | Perdido | GREAT WHITE GA022 | WHOLE COMPLETION EVENT |  | 2017-01-21 | 2017-03-16 | 2015 | 2016 | 54
DVA | Perdido | GREAT WHITE GA015 | WHOLE DRILLING EVENT | GA015_P D&C | 2017-03-16 | 2017-08-07 | 2017 | 2017 | 144
DVA | Perdido | GREAT WHITE GA015 | WHOLE COMPLETION EVENT |  | 2017-08-07 | 2017-10-22 | 2016 | 2016 | 76
DVA | Perdido | PERDIDO SBS 2017 | RIG - MAINTENAINCE | SBS 2017 | 2017-10-22 | 2017-11-11 | 2017 | 2017 | 20
DVA | Perdido | PERDIDO WORKOVER/INTERVENTION 2017 | WORKOVER | Workover / Intervention 2017 | 2017-11-11 | 2017-12-02 | 2017 | 2017 | 21
DVA | Perdido | PERDIDO ARM 2017 | RIG - MAINTENAINCE | ARM 2017 | 2017-12-02 | 2017-12-16 | 2017 | 2017 | 14
DVA | Perdido | GREAT WHITE GA005 | WHOLE DRILLING EVENT | GA005_I D&C | 2017-12-16 | 2018-03-26 | 2017 | 2018 | 100
DVA | Perdido | GREAT WHITE GA005 | WHOLE COMPLETION EVENT |  | 2018-03-26 | 2018-05-20 | 2014 | 2014 | 55
DVA | Perdido | PERDIDO ARM 2018 | RIG - MAINTENAINCE | SBS 2018 | 2018-05-20 | 2018-06-25 | 2018 | 2018 | 36
DVA | Perdido | PERDIDO WORKOVER/INTERVENTION 2018 | WORKOVER | Workover / Intervention 2018 | 2018-06-25 | 2018-07-16 | 2018 | 2018 | 21
DVA | Perdido | PERDIDO ARM 2018 | RIG - MAINTENAINCE | ARM 2018 | 2018-07-16 | 2018-07-28 | 2018 | 2018 | 12
DVA | Perdido | PERDIDO D&C RISER DOWNTIME 2018 | RIG - RISER MAINTENANCE (TLP/SPAR) | D&C Riser Downtime 2018 | 2018-07-28 | 2018-08-27 | 2018 | 2018 | 30
DVA | Perdido | GREAT WHITE GA013 | COM - DE-COMPLETION | GA013 Slot Recovery | 2018-08-27 | 2018-09-29 | 2018 | 2018 | 33
DVA | Perdido | GREAT WHITE GA013 | WHOLE DRILLING EVENT | GA013ST_P D&C | 2018-09-29 | 2018-12-17 | 2018 | 2018 | 79
DVA | Perdido | GREAT WHITE GA013 | WHOLE COMPLETION EVENT |  | 2018-12-17 | 2019-02-09 | 2016 | 2016 | 54
DVA | Perdido | GREAT WHITE GA021 | WHOLE DRILLING EVENT | GA021_I D&C | 2019-02-09 | 2019-05-20 | 2019 | 2019 | 100
DVA | Perdido | GREAT WHITE GA021 | WHOLE COMPLETION EVENT |  | 2019-05-20 | 2019-07-14 | 2016 | 2016 | 55
DVA | Perdido | PERDIDO SBS 2019 | RIG - MAINTENAINCE | SBS 2019 | 2019-07-14 | 2019-08-19 | 2019 | 2019 | 36
DVA | Perdido | PERDIDO ARM 2019 | RIG - MAINTENAINCE | ARM 2019 | 2019-08-19 | 2019-08-31 | 2019 | 2019 | 12
DVA | Perdido | PERDIDO WORKOVER/INTERVENTION 2019 | WORKOVER | Workover / Intervention 2019 | 2019-08-31 | 2019-09-21 | 2019 | 2019 | 21
DVA | Perdido | GREAT WHITE GA003 | WHOLE DRILLING EVENT | GA003_P D&C | 2019-09-21 | 2020-01-29 | 2019 | 2020 | 130
DVA | Perdido | GREAT WHITE GA003 | WHOLE COMPLETION EVENT |  | 2020-01-29 | 2020-03-01 | 2017 | 2017 | 32
DVA | Perdido | GREAT WHITE GA016 | WHOLE DRILLING EVENT | GA016_P D&C | 2020-03-01 | 2020-05-24 | 2020 | 2020 | 84
DVA | Perdido | GREAT WHITE GA016 | WHOLE COMPLETION EVENT |  | 2020-05-24 | 2020-07-17 | 2017 | 2017 | 54
DVA | Auger | AUGER IDLE - COLD STACK 2015 | RIG - IDLE | Rig Idle - cold Stack | 2012-06-13 | 2015-03-15 | 2012 | 2015 | 1005
DVA | Auger | AUGER RAMP UP 2015 | RIG - RAMP UP/DOWN | ramp up | 2015-03-15 | 2015-04-27 | 2015 | 2015 | 43
DVA | Auger | AUGER ANNUAL RIG INSPECTION 2015 | RIG - PREPARATION AND INSPECTION | rig annual inspection | 2015-04-27 | 2015-05-11 | 2015 | 2015 | 14
DVA | Auger | AUGER OZONA TTR PULL | n/a | Ozona TTR Pull | 2015-05-11 | 2015-06-18 | 2015 | 2015 | 38
DVA | Auger | AUGER A15 | WHOLE COMPLETION EVENT | A15 UHRCQ Sand | 2015-06-18 | 2015-09-02 | 2015 | 2015 | 76
DVA | Auger | AUGER A10 | WHOLE COMPLETION EVENT | A 10 UHRC R1 Sand | 2015-09-02 | 2015-11-07 | 2015 | 2015 | 66
DVA | Auger | AUGER A17 | ABANDONMENT | A17 Fishing, Decomplete & riser pull | 2015-11-07 | 2016-02-23 | 2015 | 2016 | 108
DVA | Auger | AUGER RAMP DOWN 2016 | RIG - RAMP UP/DOWN | Ramp Down | 2016-02-23 | 2016-03-24 | 2016 | 2016 | 30
DVA | Auger | AUGER IDLE - COLD STACK 2016-2017 | RIG - IDLE | Rig Idle - Cold Stack | 2016-03-24 | 2017-09-22 | 2016 | 2017 | 547
DVA | Auger | AUGER RAMP UP 2018 | RIG - RAMP UP/DOWN | ramp up | 2017-09-22 | 2017-11-04 | 2017 | 2017 | 43
DVA | Auger | AUGER A11 | COM - DE-COMPLETION | A11 SR | 2017-11-04 | 2017-12-24 | 2017 | 2017 | 50
DVA | Auger | AUGER A11 | WHOLE DRILLING EVENT | A11 ST1 D&C | 2017-12-24 | 2018-08-06 | 2017 | 2018 | 225
DVA | Auger | AUGER A11 | WHOLE COMPLETION EVENT |  | 2018-08-06 | 2018-09-20 | 2014 | 2014 | 45
DVA | Auger | AUGER A20 | WHOLE COMPLETION EVENT | Auger A20 UHRC N3 | 2018-09-20 | 2018-12-08 | 2018 | 2018 | 79
DVA | Auger | AUGER A9 | COM - DE-COMPLETION | A9 Decomplete | 2018-12-08 | 2018-12-31 | 2018 | 2018 | 23
DVA | Auger | AUGER A9 | WHOLE DRILLING EVENT | A9 SHST R Sand Drill and Complete | 2018-12-31 | 2019-01-31 | 2018 | 2019 | 31
DVA | Auger | AUGER A9 | WHOLE COMPLETION EVENT |  | 2019-01-31 | 2019-03-18 | 2015 | 2015 | 46
DVA | Auger | AUGER RAMP DOWN 2019 | RIG - RAMP UP/DOWN | Shutdown Ramp Down | 2019-03-18 | 2019-04-02 | 2019 | 2019 | 15
DVA | Auger | AUGER PLATFORM SHUTDOWN 2019 | RIG - IDLE | TLP Shutdown | 2019-04-02 | 2019-05-02 | 2019 | 2019 | 30
DVA | Auger | AUGER RAMP UP 2019 | RIG - RAMP UP/DOWN | Post Shutdown Ramp Up | 2019-05-02 | 2019-05-17 | 2019 | 2019 | 15
DVA | Auger | AUGER A18 | COM - DE-COMPLETION | A18 Decomplete | 2019-05-17 | 2019-06-09 | 2019 | 2019 | 23
DVA | Auger | AUGER A18 | WHOLE DRILLING EVENT | A 18 SHST R4/R5/R6 Drill and Complete | 2019-06-09 | 2019-07-10 | 2019 | 2019 | 31
DVA | Auger | AUGER A18 | WHOLE COMPLETION EVENT |  | 2019-07-10 | 2019-08-25 | 2016 | 2016 | 46
DVA | Auger | AUGER A20 | COM - DE-COMPLETION | A20 Decomplete | 2019-08-25 | 2019-09-17 | 2019 | 2019 | 23
DVA | Auger | AUGER A20 ST1 | WHOLE DRILLING EVENT | A20 SHST R1/2 Res B Drill and Complete | 2019-09-17 | 2019-10-18 | 2019 | 2019 | 31
DVA | Auger | AUGER A20 ST1 | WHOLE COMPLETION EVENT |  | 2019-10-18 | 2019-11-30 | 2015 | 2015 | 43
DVA | Auger | AUGER RAMP DOWN 2020 | RIG - RAMP UP/DOWN | Ramp Down | 2019-11-30 | 2019-12-30 | 2019 | 2019 | 30
DVA | Auger | AUGER IDLE - WARM STACK 2020 | RIG - IDLE | Rig Idle - Warm Stack | 2019-12-30 | 2020-01-01 | 2019 | 2020 | 2
DVA | Brutus | BRUTUS A1 ST4 | WHOLE DRILLING EVENT | A-1ST4 SHST to G1A RCn | 2014-10-21 | 2014-11-15 | 2014 | 2014 | 25
DVA | Brutus | BRUTUS A1 ST4 | WHOLE COMPLETION EVENT |  | 2014-11-15 | 2014-12-17 | 2015 | 2016 | 32
DVA | Brutus | BRUTUS A2 ST1 | COM - DE-COMPLETION | Decomplete A2 | 2014-12-17 | 2015-01-23 | 2014 | 2015 | 37
DVA | Brutus | BRUTUS RAMP DOWN 2015 | RIG - RAMP UP/DOWN | RAMP DOWN | 2015-01-23 | 2015-02-14 | 2015 | 2015 | 22
DVA | Brutus | BRUTUS IDLE - WARM STACK 2015 | RIG - IDLE | Rig Idle Warm Stack | 2015-02-14 | 2015-05-18 | 2015 | 2015 | 93
DVA | Brutus | BRUTUS IDLE - COLD STACK 2015 | RIG - IDLE | Rig Idle Cold Stack | 2015-05-18 | 2015-09-22 | 2015 | 2015 | 127
DVA | Brutus | BRUTUS PLATFORM SHUTDOWN 2015 | RIG - IDLE | TLP Shutdown | 2015-09-22 | 2015-10-13 | 2015 | 2015 | 21
DVA | Brutus | BRUTUS IDLE - COLD STACK 2015-2016 | RIG - IDLE | Rig Idle Cold Stack | 2015-10-13 | 2016-01-12 | 2015 | 2016 | 91
DVA | Brutus | BRUTUS RAMP UP 2016 | RIG - RAMP UP/DOWN | RAMP UP | 2016-01-12 | 2016-02-26 | 2016 | 2016 | 45
DVA | Brutus | BRUTUS RIG INSPECTION 2016 | RIG - PREPARATION AND INSPECTION | RIG INSPECTION | 2016-02-26 | 2016-03-07 | 2016 | 2016 | 10
DVA | Brutus | BRUTUS A6 ST2 | WHOLE DRILLING EVENT | A-6ST2 SHST E9 RCb D&C | 2016-03-07 | 2016-04-02 | 2016 | 2016 | 26
DVA | Brutus | BRUTUS A6 ST2 | WHOLE COMPLETION EVENT |  | 2016-04-02 | 2016-05-25 | 2019 | 2019 | 53
DVA | Brutus | BRUTUS COIL TUBING JOB 2016 | WRFM/RST - RESERVOIR WELLBORE CLEANOUTS | Statistical Coil Tubing Job 2016 | 2016-05-25 | 2016-06-18 | 2016 | 2016 | 24
DVA | Brutus | BRUTUS A4 ST5 | COM - DE-COMPLETION | Decomplete A-4ST5 | 2016-06-18 | 2016-08-09 | 2016 | 2016 | 52
DVA | Brutus | BRUTUS A4 ST6 | WHOLE DRILLING EVENT | A-4ST6 SHST to J2 RU2 D&C | 2016-08-09 | 2016-10-18 | 2016 | 2016 | 70
DVA | Brutus | BRUTUS A4 ST6 | WHOLE COMPLETION EVENT |  | 2016-10-18 | 2016-12-13 | 2015 | 2015 | 56
DVA | Brutus | BRUTUS A8 ST2 | COM - DE-COMPLETION | Decomplete A-8ST2 | 2016-12-13 | 2017-02-03 | 2016 | 2017 | 52
DVA | Brutus | BRUTUS RIG INSPECTION 2017 | RIG - PREPARATION AND INSPECTION | RIG INSPECTION | 2017-02-03 | 2017-02-13 | 2017 | 2017 | 10
DVA | Brutus | BRUTUS A2 ST1 | WHOLE DRILLING EVENT | A-2T1SHST To E Sands D&C | 2017-02-13 | 2017-03-15 | 2017 | 2017 | 30
DVA | Brutus | BRUTUS A2 ST1 | WHOLE COMPLETION EVENT |  | 2017-03-15 | 2017-05-04 | 2016 | 2016 | 50
DVA | Brutus | BRUTUS RAMP DOWN 2017 | RIG - RAMP UP/DOWN | RAMP DOWN | 2017-05-04 | 2017-05-26 | 2017 | 2017 | 22
DVA | Brutus | BRUTUS IDLE - WARM STACK 2017 | RIG - IDLE | Rig Idle Warm Stack | 2017-05-26 | 2017-09-08 | 2017 | 2017 | 105
DVA | Brutus | BRUTUS PLATFORM SHUTDOWN 2018 | RIG - IDLE | TLP Shutdown | 2017-09-08 | 2017-09-29 | 2017 | 2017 | 21
DVA | Brutus | BRUTUS IDLE - WARM STACK 2018-2020 | RIG - IDLE | Rig Idle Warm Stack | 2017-09-29 | 2020-01-08 | 2017 | 2020 | 831
DVA | Ursa | URSA A10 | COM - UPPER COMPLETION | A10 Smart_K1K0 | 2014-07-09 | 2014-11-02 | 2014 | 2014 | 116
DVA | Ursa | URSA RAMP DOWN 2014 | RIG - RAMP UP/DOWN | Ramp Down | 2014-11-02 | 2014-11-30 | 2014 | 2014 | 28
DVA | Ursa | URSA IDLE - WARM STACK 2015 | RIG - IDLE | Idle Warm Stack | 2014-11-30 | 2015-04-10 | 2014 | 2015 | 131
DVA | Ursa | URSA IDLE - COLD STACK 2015 | RIG - IDLE | Idle Cold Stack | 2015-04-10 | 2015-05-10 | 2015 | 2015 | 30
DVA | Ursa | URSA PLATFORM SHUTDOWN 2015 | RIG - IDLE | TLP Shutdown | 2015-05-10 | 2015-06-08 | 2015 | 2015 | 29
DVA | Ursa | URSA RIG INSPECTION & RAMP UP 2015 | RIG - PREPARATION AND INSPECTION | Rig Inspection & Ramp up | 2015-06-08 | 2015-07-08 | 2015 | 2015 | 30
DVA | Ursa | URSA A5 | WHOLE COMPLETION EVENT | A5 Smart_Q1Q2 | 2015-07-08 | 2015-12-08 | 2015 | 2015 | 153
DVA | Ursa | URSA RAMP DOWN 2016 | RIG - RAMP UP/DOWN | Ramp Down | 2015-12-08 | 2016-01-05 | 2015 | 2016 | 28
DVA | Ursa | URSA IDLE - WARM STACK 2016 | RIG - IDLE | Warm Stack -Cold Stack | 2016-01-05 | 2016-03-29 | 2016 | 2016 | 84
DVA | Ursa | URSA RAMP UP 2016 | RIG - RAMP UP/DOWN | Ramp up | 2016-03-29 | 2016-04-12 | 2016 | 2016 | 14
DVA | Ursa | URSA A12ST | COM - DE-COMPLETION | A12ST Decomplete and SR | 2016-04-12 | 2016-05-25 | 2016 | 2016 | 43
DVA | Ursa | URSA A12ST | COM - DE-COMPLETION |  | 2016-05-25 | 2016-08-13 | 2018 | 2018 | 80
DVA | Ursa | URSA A12ST | WHOLE DRILLING EVENT | A12ST_F_Block D&C | 2016-08-13 | 2017-02-25 | 2016 | 2017 | 196
DVA | Ursa | URSA A12ST | WHOLE COMPLETION EVENT |  | 2017-02-25 | 2017-05-31 | 2018 | 2019 | 95
DVA | Ursa | URSA RAMP DOWN 2017 | RIG - RAMP UP/DOWN | Ramp Down | 2017-05-31 | 2017-06-28 | 2017 | 2017 | 28
DVA | Ursa | URSA IDLE - WARM STACK 2017 | RIG - IDLE | Idle Warm Stack | 2017-06-28 | 2017-08-20 | 2017 | 2017 | 53
DVA | Ursa | URSA PLATFORM SHUTDOWN 2017 | RIG - IDLE | Tlp Shutdown | 2017-08-20 | 2017-08-27 | 2017 | 2017 | 7
DVA | Ursa | URSA IDLE - WARM STACK 2017-2018 | RIG - IDLE | Idle Warm Stack | 2017-08-27 | 2017-11-11 | 2017 | 2017 | 76
DVA | Ursa | URSA IDLE - COLD STACK 2018 | RIG - IDLE | Idle Cold Stack | 2017-11-11 | 2018-05-21 | 2017 | 2018 | 191
DVA | Ursa | URSA PLATFORM SHUTDOWN 2018 | RIG - IDLE | Tlp Shutdown | 2018-05-21 | 2018-06-16 | 2018 | 2018 | 26
DVA | Ursa | URSA IDLE - COLD STACK 2018-2020 | RIG - IDLE | Idle Cold Stack | 2018-06-16 | 2020-02-20 | 2018 | 2020 | 614
DVA | Ram Powell | RAM POWELL A7 | WHOLE DRILLING EVENT | A-7 New Well D&C | 2014-11-28 | 2015-05-08 | 2014 | 2015 | 161
DVA | Ram Powell | RAM POWELL A7 | WHOLE COMPLETION EVENT |  | 2015-05-08 | 2015-06-12 | 2020 | 2021 | 35
DVA | Ram Powell | RAM POWELL A19 PA | ABANDONMENT | A-19 P&A | 2015-06-12 | 2015-09-12 | 2015 | 2015 | 92
DVA | Ram Powell | RAM POWELL A14 PA | ABANDONMENT | A-14 P&A | 2015-09-12 | 2015-12-13 | 2015 | 2015 | 92
DVA | Ram Powell | RAM POWELL PLATFORM SHUTDOWN 2016 | RIG - IDLE | 2015 Asset Integrity Shutdown | 2015-12-13 | 2016-01-04 | 2015 | 2016 | 22
DVA | Ram Powell | RAM POWELL A15 | WHOLE DRILLING EVENT | A-15 D&C | 2016-01-04 | 2016-07-06 | 2016 | 2016 | 184
DVA | Ram Powell | RAM POWELL A15 | WHOLE COMPLETION EVENT |  | 2016-07-06 | 2016-11-10 | 2016 | 2016 | 127
DVA | Ram Powell | RAM POWELL A13 PA | COM - DE-COMPLETION | A-13 P&A | 2016-11-10 | 2017-02-17 | 2016 | 2017 | 99
DVA | Ram Powell | RAM POWELL RIG DEMOB | RIG - DEMOBILISATION | Demob | 2017-02-17 | 2017-03-19 | 2017 | 2017 | 30
DVA | Ram Powell | RAM POWELL PLATFORM SHUTDOWN | n/a | 2017 Asset Integrity Shutdown | 2017-03-19 | 2017-04-14 | 2017 | 2017 | 26
DVA | Mars | MARS A3 Inj BHST | WHOLE DRILLING EVENT | A-3 Hz Inj BHST D&C | 2014-03-20 | 2015-02-19 | 2014 | 2015 | 336
DVA | Mars | MARS A3 Inj BHST | WHOLE COMPLETION EVENT |  | 2015-02-19 | 2015-03-16 | 2018 | 2018 | 25
DVA | Mars | MARS 5 YEAR RIG INSPECTION 2015 | RIG - PREPARATION AND INSPECTION | 5 Year-Rig Inspection | 2015-03-16 | 2015-04-05 | 2015 | 2015 | 20
DVA | Mars | MARS PLATFORM SHUTDOWN 2015 | RIG - IDLE | Pre S/D | 2015-04-05 | 2015-06-14 | 2015 | 2015 | 70
DVA | Mars | MARS PLATFORM SHUTDOWN 2015 | RIG - IDLE | Corridor SD | 2015-06-14 | 2015-07-23 | 2015 | 2015 | 39
DVA | Mars | MARS PLATFORM SHUTDOWN 2015 | RIG - IDLE | Post S/D | 2015-07-23 | 2015-09-01 | 2015 | 2015 | 40
DVA | Mars | MARS 5 YEAR RIG INSPECTION 2015 | RIG - PREPARATION AND INSPECTION | 5 Year-Rig Inspection | 2015-09-01 | 2015-10-01 | 2015 | 2015 | 30
DVA | Mars | MARS A8 | COM - DE-COMPLETION | A8 PA | 2015-10-01 | 2015-10-25 | 2015 | 2015 | 24
DVA | Mars | MARS A8 | WHOLE COMPLETION EVENT | A8 UHRC | 2015-10-25 | 2015-12-20 | 2015 | 2015 | 56
DVA | Mars | MARS A6 | COM - DE-COMPLETION | A-6 PA | 2015-12-20 | 2016-02-05 | 2015 | 2016 | 47
DVA | Mars | MARS A6 | WHOLE COMPLETION EVENT | A-6 F1 UHRC | 2016-02-05 | 2016-04-13 | 2016 | 2016 | 68
DVA | Mars | MARS A20 O2 INJ HZ | COM - DE-COMPLETION | A20 K PA | 2016-04-13 | 2016-05-20 | 2016 | 2016 | 37
DVA | Mars | MARS PLATFORM SHUTDOWN 2016 | RIG - IDLE | Pre S/D | 2016-05-20 | 2016-06-19 | 2016 | 2016 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2016 | RIG - IDLE | Corridor SD | 2016-06-19 | 2016-07-19 | 2016 | 2016 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2016 | RIG - IDLE | Post S/D | 2016-07-19 | 2016-08-18 | 2016 | 2016 | 30
DVA | Mars | MARS ANNUAL RIG INSPECTION 2016 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2016-08-18 | 2016-08-30 | 2016 | 2016 | 12
DVA | Mars | MARS A20 O2 INJ HZ | COM - DE-COMPLETION | A20 K SR | 2016-08-30 | 2016-11-08 | 2016 | 2016 | 70
DVA | Mars | MARS A20 O2 INJ HZ | WHOLE DRILLING EVENT | O2 Injector Hz Drill | 2016-11-08 | 2017-03-11 | 2016 | 2017 | 123
DVA | Mars | MARS RISER PULL/RERUN 2017 | RIG - RISER MAINTENANCE (TLP/SPAR) | Riser Pull | 2017-03-11 | 2017-03-23 | 2017 | 2017 | 12
DVA | Mars | MARS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Pre S/D | 2017-03-23 | 2017-04-22 | 2017 | 2017 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Corridor SD | 2017-04-22 | 2017-05-22 | 2017 | 2017 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Post S/D | 2017-05-22 | 2017-06-21 | 2017 | 2017 | 30
DVA | Mars | MARS ANNUAL RIG INSPECTION 2017 | RIG - PREPARATION AND INSPECTION | Annual Rig Inspection | 2017-06-21 | 2017-07-03 | 2017 | 2017 | 12
DVA | Mars | MARS RISER PULL/RERUN 2017 | RIG - RISER MAINTENANCE (TLP/SPAR) | Riser Rerun | 2017-07-03 | 2017-07-18 | 2017 | 2017 | 15
DVA | Mars | MARS A20 O2 INJ HZ | WHOLE DRILLING EVENT | O2 Injector Hz Drill and complete | 2017-07-18 | 2017-11-10 | 2017 | 2017 | 115
DVA | Mars | MARS A20 O2 INJ HZ | WHOLE COMPLETION EVENT |  | 2017-11-10 | 2017-12-22 | 2018 | 2019 | 42
DVA | Mars | MARS A18 | WHOLE COMPLETION EVENT | A18 UHRC D8.8/D10 | 2017-12-22 | 2018-04-23 | 2017 | 2018 | 122
DVA | Mars | MARS A19 | COM - DE-COMPLETION | A19 SHST I2_RA | 2018-04-23 | 2018-05-28 | 2018 | 2018 | 35
DVA | Mars | MARS A19 | WHOLE DRILLING EVENT |  | 2018-05-28 | 2018-07-07 | 2019 | 2019 | 40
DVA | Mars | MARS A19 | WHOLE COMPLETION EVENT |  | 2018-07-07 | 2018-08-28 | 2019 | 2020 | 52
DVA | Mars | MARS ANNUAL RIG INSPECTION 2018 | RIG - PREPARATION AND INSPECTION | Annual Rig Inspection | 2018-08-28 | 2018-09-09 | 2018 | 2018 | 12
DVA | Mars | MARS A16 M2 INJ | COM - DE-COMPLETION | A16 PA & SR | 2018-09-09 | 2018-10-14 | 2018 | 2018 | 35
DVA | Mars | MARS A16 M2 INJ | COM - DE-COMPLETION |  | 2018-10-14 | 2018-12-23 | 2020 | 2020 | 70
DVA | Mars | MARS A16 M2 INJ | WHOLE DRILLING EVENT | M2 Inj Drill | 2018-12-23 | 2019-04-20 | 2018 | 2019 | 118
DVA | Mars | MARS RISER PULL/RERUN 2019 | RIG - RISER MAINTENANCE (TLP/SPAR) | Riser Pull | 2019-04-20 | 2019-05-02 | 2019 | 2019 | 12
DVA | Mars | MARS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Pre S/D | 2019-05-02 | 2019-06-01 | 2019 | 2019 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Corridor SD | 2019-06-01 | 2019-07-01 | 2019 | 2019 | 30
DVA | Mars | MARS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Post S/D | 2019-07-01 | 2019-08-15 | 2019 | 2019 | 45
DVA | Mars | MARS ANNUAL RIG INSPECTION 2019 | RIG - PREPARATION AND INSPECTION | Annual Rig Inspection | 2019-08-15 | 2019-08-27 | 2019 | 2019 | 12
DVA | Mars | MARS RISER PULL/RERUN 2019 | RIG - RISER MAINTENANCE (TLP/SPAR) | Riser Run | 2019-08-27 | 2019-09-11 | 2019 | 2019 | 15
DVA | Mars | MARS A16 M2 INJ | WHOLE DRILLING EVENT | M2 Inj Drill and Complete | 2019-09-11 | 2020-01-28 | 2019 | 2020 | 139
DVA | Mars | MARS A16 M2 INJ | WHOLE COMPLETION EVENT |  | 2020-01-28 | 2020-03-13 | 2020 | 2020 | 45
DVA | Mars | MARS A10 | COM - DE-COMPLETION | A10 PA | 2020-03-13 | 2020-06-04 | 2020 | 2020 | 83
DVA | Mars | MARS A10 | WHOLE COMPLETION EVENT | A10 UHRC | 2020-06-04 | 2020-07-26 | 2020 | 2020 | 52
DVA | Mars | MARS A9 | COM - DE-COMPLETION | A9 PA & SR | 2020-07-26 | 2020-11-08 | 2020 | 2020 | 105
DVA | Olympus | OLYMPUS MB-08 | WHOLE DRILLING EVENT | MB08 H1 Attic D&C | 2015-08-01 | 2016-01-30 | 2015 | 2016 | 182
DVA | Olympus | OLYMPUS MB-08 | WHOLE COMPLETION EVENT |  | 2016-01-30 | 2016-03-28 | 2016 | 2016 | 58
DVA | Olympus | OLYMPUS RIG SHUTDOWN 2016 | RIG - IDLE | Rig Shutdown | 2016-03-28 | 2016-04-20 | 2016 | 2016 | 23
DVA | Olympus | OLYMPUS ANNUAL RIG INSPECTION 2016 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2016-04-20 | 2016-04-27 | 2016 | 2016 | 7
DVA | Olympus | OLYMPUS MB-01 | WHOLE DRILLING EVENT | MB-01 W3 Gold D&C | 2016-04-27 | 2016-12-03 | 2016 | 2016 | 220
DVA | Olympus | OLYMPUS MB-01 | WHOLE COMPLETION EVENT |  | 2016-12-03 | 2017-02-06 | 2019 | 2020 | 65
DVA | Olympus | OLYMPUS MB-07 TITANIUM | WHOLE DRILLING EVENT | MB07 X1 Titanium Drill | 2017-02-06 | 2017-04-07 | 2017 | 2017 | 60
DVA | Olympus | OLYMPUS ANNUAL RIG INSPECTION 2017 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2017-04-07 | 2017-04-14 | 2017 | 2017 | 7
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Pre S/D | 2017-04-14 | 2017-05-02 | 2017 | 2017 | 18
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Corridor SD | 2017-05-02 | 2017-05-23 | 2017 | 2017 | 21
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2017 | RIG - IDLE | Post S/D | 2017-05-23 | 2017-06-10 | 2017 | 2017 | 18
DVA | Olympus | OLYMPUS MB-07 TITANIUM | WHOLE DRILLING EVENT | MB07 X1 Titanium Drill | 2017-06-10 | 2017-12-06 | 2017 | 2017 | 179
DVA | Olympus | OLYMPUS MB-07 TITANIUM | WHOLE COMPLETION EVENT | MB07 X1 Titanium Complete | 2017-12-06 | 2018-02-12 | 2017 | 2018 | 68
DVA | Olympus | OLYMPUS MB-03 | WHOLE DRILLING EVENT | MB-23 E2 mid dip HZ Drill | 2018-02-12 | 2018-07-29 | 2018 | 2018 | 167
DVA | Olympus | OLYMPUS ANNUAL RIG INSPECTION 2018 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2018-07-29 | 2018-08-05 | 2018 | 2018 | 7
DVA | Olympus | OLYMPUS MB-03 | WHOLE COMPLETION EVENT | MB-23 E2 mid dip HZ Complete | 2018-08-05 | 2018-09-24 | 2018 | 2018 | 50
DVA | Olympus | OLYMPUS MB-05 W4/W4.5 PYRITE | WHOLE DRILLING EVENT | W4/W4.5 Pyrite Drill | 2018-09-24 | 2019-04-22 | 2018 | 2019 | 210
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Pre S/D | 2019-04-22 | 2019-05-10 | 2019 | 2019 | 18
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Corridor SD | 2019-05-10 | 2019-05-31 | 2019 | 2019 | 21
DVA | Olympus | OLYMPUS PLATFORM SHUTDOWN 2019 | RIG - IDLE | Post S/D | 2019-05-31 | 2019-06-18 | 2019 | 2019 | 18
DVA | Olympus | OLYMPUS ANNUAL RIG INSPECTION 2019 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2019-06-18 | 2019-06-25 | 2019 | 2019 | 7
DVA | Olympus | OLYMPUS MB-05 W4/W4.5 PYRITE | WHOLE COMPLETION EVENT | W4/W4.5 Pyrite Complete | 2019-06-25 | 2019-08-26 | 2019 | 2019 | 62
DVA | Olympus | OLYMPUS MB-06 T2_N GREEN BICE | WHOLE DRILLING EVENT | T2_N Green Bice Drill | 2019-08-26 | 2020-05-24 | 2019 | 2020 | 272
DVA | Olympus | OLYMPUS ANNUAL RIG INSPECTION 2020 | RIG - PREPARATION AND INSPECTION | Rig Inspection | 2020-05-24 | 2020-07-08 | 2020 | 2020 | 45
DVA | Olympus | OLYMPUS MB-06 T2_N GREEN BICE | WHOLE COMPLETION EVENT | T2_N Green Bice Complete | 2020-07-08 | 2020-09-04 | 2020 | 2020 | 58
MODU | SEDCO 702 | Bonga 05 | WELL INTERVENTION | B-05 - CT Intervention (Acidiisation) | 2015-01-01 | 2015-01-03 | 2015 | 2015 | 2
MODU | SEDCO 702 | Bonga 670b4 w2 | SUSPEND | Suspension of B-20 for 670b4 w2 (CT cleanout) - 1 | 2015-01-03 | 2015-01-08 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 29 | WELL INTERVENTION | B-29 - CT Intervention (Acidiisation) | 2015-01-08 12:30 | 2015-01-12 07:00 | 2015 | 2015 | 3.7708
MODU | SEDCO 702 | Bonga 670b4 w2 | SUSPEND | Suspension of B-20 for 670b4 w2 (CT cleanout) - 2 | 2015-01-12 | 2015-01-13 | 2015 | 2015 | 1
MODU | SEDCO 702 | Bonga 690 p5 | SUSPEND | Suspension for 690 p5 - 1 (B-19) | 2015-01-13 | 2015-01-21 | 2015 | 2015 | 8
MODU | SEDCO 702 | Bonga 670b4 p3 | SUSPEND | Suspension of B-09 for 670b4 p3 (B-09) | 2015-01-21 | 2015-01-23 | 2015 | 2015 | 2
MODU | SEDCO 702 | Bonga 690 p5 | SUSPEND | Suspension for 690 p5 - 2 (B-19) | 2015-01-23 | 2015-01-29 | 2015 | 2015 | 6
MODU | SEDCO 702 | Bonga BM 710 p4 | SUSPEND | Suspension for 710 p4 (B-18) | 2015-01-29 | 2015-02-03 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 670b10 w1 | DRL - INTERM. | BMPh3-670b10 w1 - Drilling to 9-5/8" casing | 2015-02-03 | 2015-02-17 | 2015 | 2015 | 14
MODU | SEDCO 702 | Bonga 670b10 w1 | DRL - PROD ONLY | BMPh3-670b10 w1 - 8-1/2" Section | 2015-02-17 | 2015-02-21 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 670b10 w1 | COM - LOWER COMPLETION | BMPh3-670b10 w1 - Lower Completion | 2015-02-21 | 2015-02-26 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 670b10 w1 | COM - UPPER COMPLETION | BMPh3-670b10 w1 - Upper Completion | 2015-02-26 | 2015-03-03 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 670b10 p1 | COM - UPPER COMPLETION | BMPh3-670b10 p1 - Upper Completion | 2015-03-03 | 2015-03-10 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 689 p1 | COM - UPPER COMPLETION | BMPh3-689 p1 - Upper Completion | 2015-03-10 | 2015-03-17 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga BM 709 p1 | COM - UPPER COMPLETION | BMPh2-709 p1 - Upper Completion | 2015-03-17 | 2015-03-27 | 2015 | 2015 | 10
MODU | SEDCO 702 | Bonga 689 w1 | DRL - TOP HOLE ONLY | BMPh3-689 w1 (Top Hole) | 2015-03-27 | 2015-03-30 | 2015 | 2015 | 3
MODU | SEDCO 702 | Bonga 803 p5 | DRL - TOP HOLE ONLY | BMPh3-803 p5 (Top Hole) | 2015-03-30 | 2015-04-03 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 690 p5 | DRL - TOP HOLE ONLY | BMPh3-690 p5 (Top Hole) | 2015-04-03 | 2015-04-06 | 2015 | 2015 | 3
MODU | SEDCO 702 | Bonga 803 w5 | DRL - TOP HOLE ONLY | BMPh3-803 w5 (Top Hole) | 2015-04-06 | 2015-04-10 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga BM 710 p4 | SUSPEND | Suspension for 710 p4 (B-18) - 2 | 2015-04-10 | 2015-04-18 | 2015 | 2015 | 8
MODU | SEDCO 702 | Bonga 29 | SUSPEND | Suspension of B-29 (For Xtree harvest) | 2015-04-18 | 2015-04-23 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 08 | SUSPEND | Suspension of B-08 (For Xtree harvest) | 2015-04-23 | 2015-04-30 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 689 w1 | DRL - INTERM. | BMPh3-689 w1 - Drilling to 9-5/8" Csg | 2015-04-30 | 2015-05-18 | 2015 | 2015 | 18
MODU | SEDCO 702 | Bonga 689 w1 | DRL - PROD ONLY | BMPh3-689 w1 - 8-1/2" Hole | 2015-05-18 | 2015-05-22 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 689 w1 | COM - LOWER COMPLETION | BMPh3-689 w1 - Lower Completion | 2015-05-22 | 2015-05-29 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 689 w1 | COM - UPPER COMPLETION | BMPh3-689 w1 - Upper Completion | 2015-05-29 | 2015-06-05 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 803 p5 | DRL - INTERM. | BMPh3-803 p5 Drilling to 9-5/8" Csg | 2015-06-05 | 2015-06-30 | 2015 | 2015 | 25
MODU | SEDCO 702 | Bonga 803 p5 | DRL - PROD ONLY | BMPh3-803 p5 - 8-1/2" Hole | 2015-06-30 | 2015-07-06 | 2015 | 2015 | 6
MODU | SEDCO 702 | Bonga 803 p5 | COM - LOWER COMPLETION | BMPh3-803 p5 - Lower Completion | 2015-07-06 | 2015-07-13 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 690 p5 | DRL - INTERM. | BMPh3-690 p5 - Drilling to 9-5/8" Csg | 2015-07-13 | 2015-08-07 | 2015 | 2015 | 25
MODU | SEDCO 702 | Bonga 690 p5 | DRL - PROD ONLY | BMPh3-690 p5 - 8-1/2" Section | 2015-08-07 | 2015-08-13 | 2015 | 2015 | 6
MODU | SEDCO 702 | Bonga 690 p5 | COM - LOWER COMPLETION | BMPh3-690 p5 - Lower Completion | 2015-08-13 | 2015-08-20 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 803 w5 | DRL - INTERM. | BMPh3-803 w5 - Drilling to 9-5/8" csg | 2015-08-20 | 2015-09-14 | 2015 | 2015 | 25
MODU | SEDCO 702 | Bonga 803 w5 | DRL - PROD ONLY | BMPh3-803 w5 - 8-1/2" Section | 2015-09-14 | 2015-09-20 | 2015 | 2015 | 6
MODU | SEDCO 702 | Bonga 803 w5 | COM - LOWER COMPLETION | BMPh3-803 w5 - Lower Completion | 2015-09-20 | 2015-09-27 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 803 p5 | COM - UPPER COMPLETION | BMPh3-803 p5 - Upper Completion | 2015-09-27 | 2015-10-04 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 690 p5 | COM - UPPER COMPLETION | BMPh3-690 p5 - Upper Completion | 2015-10-04 | 2015-10-11 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 803 w5 | COM - UPPER COMPLETION | BMPh3-803 w5 - Upper Completion | 2015-10-11 | 2015-10-21 | 2015 | 2015 | 10
MODU | SEDCO 702 | Bonga 803 w4 | DRL - TOP HOLE ONLY | BMph2 - 803 w4 - (Top Hole) | 2015-10-21 | 2015-10-25 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 670b4 p3 | DRL - TOP HOLE ONLY | BMPh3-670b4 p3 - (TopHole) | 2015-10-25 | 2015-10-30 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 670b4 w2 | DRL - TOP HOLE ONLY | BMPh3-670b4 w2 - (TopHole) | 2015-10-30 | 2015-11-04 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 702 w8 | DRL - TOP HOLE ONLY | BMph2 - 702 w8 - (Top Hole) | 2015-11-04 | 2015-11-08 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 803 w4 | DRL - INTERM. | BMph2-803 w4 - Drilling to 9-5/8" csg | 2015-11-08 | 2015-12-06 | 2015 | 2015 | 28
MODU | SEDCO 702 | Bonga 803 w4 | DRL - PROD ONLY | BMph2-803 w4 - 8-1/2" Hole | 2015-12-06 | 2015-12-10 | 2015 | 2015 | 4
MODU | SEDCO 702 | Bonga 803 w4 | COM - LOWER COMPLETION | BMph2-803 w4 - Lower Completion | 2015-12-10 | 2015-12-15 | 2015 | 2015 | 5
MODU | SEDCO 702 | Bonga 803 w4 | COM - UPPER COMPLETION | BMph2-803 w4 - Upper Completion | 2015-12-15 | 2015-12-22 | 2015 | 2015 | 7
MODU | SEDCO 702 | Bonga 670b4 p3 | DRL - INTERM. | BMPh3-670b4 p3 - Drilling to 9-5/8" Csg | 2015-12-22 | 2016-01-01 | 2015 | 2016 | 10
MODU | SEDCO 702 | Bonga 670b4 p3 | DRL - INTERM. | BMPh3-670b4 p3 - Drilling to 9-5/8" Csg | 2016-01-01 | 2016-01-06 | 2016 | 2016 | 5
MODU | SEDCO 702 | Bonga 670b4 p3 | DRL - PROD ONLY | BMPh3-670b4 p3 - 8-1/2" Hole | 2016-01-06 | 2016-01-12 | 2016 | 2016 | 6
MODU | SEDCO 702 | Bonga 670b4 p3 | COM - LOWER COMPLETION | BMPh3-670b4 p3 - Lower Completion | 2016-01-12 | 2016-01-19 | 2016 | 2016 | 7
MODU | SEDCO 702 | Bonga 670b4 w2 | DRL - INTERM. | BMPh3-670b4 w2 - Drilling to 9-5/8" Csg | 2016-01-19 | 2016-02-03 | 2016 | 2016 | 15
MODU | SEDCO 702 | Bonga 670b4 w2 | DRL - PROD ONLY | BMPh3-670b4 w2 - 8-1/2"hole | 2016-02-03 | 2016-02-09 | 2016 | 2016 | 6
MODU | SEDCO 702 | Bonga 670b4 w2 | COM - LOWER COMPLETION | BMPh3-670b4 w2 - Lower Completion | 2016-02-09 | 2016-02-16 | 2016 | 2016 | 7
MODU | SEDCO 702 | Bonga 670b4 w2 | COM - UPPER COMPLETION | BMPh3-670b4 w2 - Upper Completion | 2016-02-16 | 2016-02-26 | 2016 | 2016 | 10
MODU | SEDCO 702 | Bonga 670b4 p3 | COM - UPPER COMPLETION | BMPh3-670b4 p3 - Upper Completion | 2016-02-26 | 2016-03-07 | 2016 | 2016 | 10
MODU | SEDCO 702 | Bonga 702 w8 | DRL - INTERM. | BMph2-702 w8- Drilling to 9-5/8" csg | 2016-03-07 | 2016-04-01 | 2016 | 2016 | 25
MODU | SEDCO 702 | Bonga 702 w8 | DRL - PROD ONLY | BMph2-702 w8 - 8-1/2" Hole | 2016-04-01 | 2016-04-07 | 2016 | 2016 | 6
MODU | SEDCO 702 | Bonga 702 w8 | COM - LOWER COMPLETION | BMph2-702 w8 - Lower Completion | 2016-04-07 | 2016-04-14 | 2016 | 2016 | 7
MODU | SEDCO 702 | Bonga 702 w8 | COM - UPPER COMPLETION | BMph2-702 w8 - Upper Completion | 2016-04-14 | 2016-04-24 | 2016 | 2016 | 10
MODU | SEDCO 702 | SEDCO 702 RIG DEMOB | RIG - DEMOBILISATION | Demobilisation of the rig | 2016-04-24 | 2016-05-08 06:15 | 2016 | 2016 | 14.2604
MODU | NG Rig 3 | NG Rig 3 MOB | RIG - MOBILISATION | Rig Prep and mobilisation | 2016-07-01 | 2016-07-22 | 2016 | 2016 | 21
MODU | NG Rig 3 | Bonga 670b10 p2 | DRL - TOP HOLE ONLY | BMPh3-670b10 p2 - (Top Hole) | 2016-07-22 | 2016-07-29 | 2016 | 2016 | 7
MODU | NG Rig 3 | Bonga 670b10 w2 | DRL - TOP HOLE ONLY | BMPh3-670b10 w2 (Top Hole) | 2016-07-29 | 2016-08-05 | 2016 | 2016 | 7
MODU | NG Rig 3 | Bonga BM 710 p4 | DRL - TOP HOLE ONLY | BMPh2-710 p4 - (Top Hole) | 2016-08-05 | 2016-08-11 | 2016 | 2016 | 6
MODU | NG Rig 3 | Bonga BM 710 w4 | DRL - TOP HOLE ONLY | BMPh2-710 w4 - (Top Hole) | 2016-08-11 | 2016-08-17 | 2016 | 2016 | 6
MODU | NG Rig 3 | Bonga 690 w5 | DRL - TOP HOLE ONLY | BMPh3-690 w5 - (Top Hole) | 2016-08-17 | 2016-08-23 | 2016 | 2016 | 6
MODU | NG Rig 3 | Bonga 670b10 p2 | DRL - INTERM. | BMPh3-670b10 p2 - Drilling to 9-5/8" Csg | 2016-08-23 | 2016-09-07 | 2016 | 2016 | 15
MODU | NG Rig 3 | Bonga 670b10 p2 | DRL - PROD ONLY | BMPh3-670b10 p2 - 8-1/2" Hole | 2016-09-07 | 2016-09-13 | 2016 | 2016 | 6
MODU | NG Rig 3 | Bonga 670b10 p2 | COM - LOWER COMPLETION | BMPh3-670b10 p2 - Lower Completion | 2016-09-13 | 2016-09-20 | 2016 | 2016 | 7
MODU | NG Rig 3 | Bonga 670b10 p2 | COM - UPPER COMPLETION | BMPh3-670b10 p2 - Upper Completion | 2016-09-20 | 2016-09-30 | 2016 | 2016 | 10
MODU | NG Rig 3 | Bonga BM 710 p4 | DRL - INTERM. | BMPh2-710 p4 - Drilling to 9-5/8" Csg | 2016-09-30 | 2016-10-25 | 2016 | 2016 | 25
MODU | NG Rig 3 | Bonga BM 710 p4 | DRL - PROD ONLY | BMPh2-710 p4 - 8-1/2" Hole | 2016-10-25 | 2016-10-31 | 2016 | 2016 | 6
MODU | NG Rig 3 | Bonga BM 710 p4 | COM - LOWER COMPLETION | BMPh2-710 p4 - Lower Completion | 2016-10-31 | 2016-11-07 | 2016 | 2016 | 7
MODU | NG Rig 3 | Bonga BM 710 p4 | COM - UPPER COMPLETION | BMPh2-710 p4 - Upper Completion | 2016-11-07 | 2016-11-17 | 2016 | 2016 | 10
MODU | NG Rig 3 | NG Rig 3 Intervention/Workover | WELL INTERVENTION | Unspecified Intervention or Workover | 2016-11-17 | 2016-12-17 | 2016 | 2016 | 30
MODU | NG Rig 3 | Bonga 690 w5 | DRL - INTERM. | BMPh3-690 w5 - Drilling to 9-5/8" Csg | 2016-12-17 | 2017-01-01 | 2016 | 2017 | 15
MODU | NG Rig 3 | Bonga 690 w5 | DRL - INTERM. | BMPh3-690 w5 - Drilling to 9-5/8" Csg | 2017-01-01 | 2017-01-11 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga 690 w5 | DRL - PROD ONLY | BMPh3-690 w5 - 8-1/2" Hole | 2017-01-11 | 2017-01-17 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 690 w5 | COM - LOWER COMPLETION | BMPh3-690 w5 - Lower Completion | 2017-01-17 | 2017-01-24 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga 690 w5 | COM - UPPER COMPLETION | BMPh3-690 w5 - Upper Completion | 2017-01-24 | 2017-02-03 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga BM 710 w4 | DRL - INTERM. | BMPh2-710 w4 - Drilling to 9-5/8" Csg | 2017-02-03 | 2017-02-18 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga BM 710 w4 | DRL - PROD ONLY | BMPh2-710 w4 - 8-1/2" Hole | 2017-02-18 | 2017-02-24 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 710 w4 | COM - LOWER COMPLETION | BMPh2-710 w4 - Lower Completion | 2017-02-24 | 2017-03-03 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga BM 710 w4 | COM - UPPER COMPLETION | BMPh2-710 w4 - Upper Completion | 2017-03-03 | 2017-03-13 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga 670b10 w2 | DRL - INTERM. | BMPh3-670b10 w2 - Drilling to 9-5/8" Csg | 2017-03-13 | 2017-03-28 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga 670b10 w2 | DRL - PROD ONLY | BMPh3-670b10 w2 - 8-1/2" Hole | 2017-03-28 | 2017-04-03 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 670b10 w2 | COM - LOWER COMPLETION | BMPh3-670b10 w2 - Lower Completion | 2017-04-03 | 2017-04-10 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga 670b10 w2 | COM - UPPER COMPLETION | BMPh3-670b10 w2 - Upper Completion | 2017-04-10 | 2017-04-20 | 2017 | 2017 | 10
MODU | NG Rig 3 | NG Rig 3 Intervention/Workover | WELL INTERVENTION | Unspecified Intervention or Workover | 2017-04-20 | 2017-05-20 | 2017 | 2017 | 30
MODU | NG Rig 3 | Bonga BM 709 W1 | DRL - INTERM. | BMPh2-709 w1 - Drilling to 9-5/8" Csg | 2017-05-20 | 2017-06-07 | 2017 | 2017 | 18
MODU | NG Rig 3 | Bonga BM 709 W1 | DRL - PROD ONLY | BMPh2-709 w1 - 8-1/2" Hole | 2017-06-07 | 2017-06-13 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 709 W1 | COM - LOWER COMPLETION | BMPh2-709 w1 - Lower Completion | 2017-06-13 | 2017-06-20 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga BM 709 W1 | COM - UPPER COMPLETION | BMPh2-709 w1 - Upper Completion | 2017-06-20 | 2017-06-30 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga 710 p5 | DRL - TOP HOLE ONLY | BMPh2b-710 p5 - (TopHole) | 2017-06-30 | 2017-07-06 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 690 p6 | DRL - TOP HOLE ONLY | BMPh2b-690 p6 - (Top Hole) | 2017-07-06 | 2017-07-12 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 690 w6 | DRL - TOP HOLE ONLY | BMPh2b-690 w6 - (Top Hole) | 2017-07-12 | 2017-07-18 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 740 SE p3 | DRL - TOP HOLE ONLY | BMPh2b-740 SE p3 (Top Hole) | 2017-07-18 | 2017-07-24 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 740 SE w3 | DRL - TOP HOLE ONLY | BMPh2b-740 SE w3 (Top Hole) | 2017-07-24 | 2017-07-30 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 710 p5 | DRL - INTERM. | BMPh2b-710 p5 - Drilling to 9-5/8" Csg | 2017-07-30 | 2017-08-14 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga 710 p5 | DRL - PROD ONLY | BMPh2b-710 p5 - 8-1/2" Hole | 2017-08-14 | 2017-08-20 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 710 p5 | COM - LOWER COMPLETION | BMPh2b-710 p5 - Lower Completion | 2017-08-20 | 2017-08-27 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga 710 p5 | COM - UPPER COMPLETION | BMPh2b-710 p5 - Upper Completion | 2017-08-27 | 2017-09-06 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga BM 690 p6 | DRL - INTERM. | BMPh2b-690 p6 - Drilling to 9-5/8" Csg | 2017-09-06 | 2017-09-21 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga BM 690 p6 | DRL - PROD ONLY | BMPh2b-690 p6 - 8-1/2" Hole | 2017-09-21 | 2017-09-27 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 690 p6 | COM - LOWER COMPLETION | BMPh2b-690 p6 - Lower Completion | 2017-09-27 | 2017-10-04 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga BM 690 p6 | COM - UPPER COMPLETION | BMPh2b-690 p6 - Upper Completion | 2017-10-04 | 2017-10-14 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga BM 690 w6 | DRL - INTERM. | BMPh2b-690 w6 - Drilling to 9-5/8" Csg | 2017-10-14 | 2017-10-29 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga BM 690 w6 | DRL - PROD ONLY | BMPh2b-690 w6 - 8-1/2" Hole | 2017-10-29 | 2017-11-04 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga BM 690 w6 | COM - LOWER COMPLETION | BMPh2b-690 w6 - Lower Completion | 2017-11-04 | 2017-11-11 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga BM 690 w6 | COM - UPPER COMPLETION | BMPh2b-690 w6 - Upper Completion | 2017-11-11 | 2017-11-21 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga 740 SE p3 | DRL - INTERM. | BMPh2b-740 SE p3 - Drilling to 9-5/8" Csg | 2017-11-21 | 2017-12-06 | 2017 | 2017 | 15
MODU | NG Rig 3 | Bonga 740 SE p3 | DRL - PROD ONLY | BMPh2b-740 SE p3 - 8-1/2" Hole | 2017-12-06 | 2017-12-12 | 2017 | 2017 | 6
MODU | NG Rig 3 | Bonga 740 SE p3 | COM - LOWER COMPLETION | BMPh2b-740 SE p3- Lower Completion | 2017-12-12 | 2017-12-19 | 2017 | 2017 | 7
MODU | NG Rig 3 | Bonga 740 SE p3 | COM - UPPER COMPLETION | BMPh2b-740 SE p3- Upper Completion | 2017-12-19 | 2017-12-29 | 2017 | 2017 | 10
MODU | NG Rig 3 | Bonga 740 SE w3 | DRL - INTERM. | BMPh2b-740 SE w3 - Drilling to 9-5/8" Csg | 2017-12-29 | 2018-01-13 | 2017 | 2018 | 15
MODU | NG Rig 3 | Bonga 740 SE w3 | DRL - PROD ONLY | BMPh2b-740 SE w3 - 8-1/2" Hole | 2018-01-13 | 2018-01-19 | 2018 | 2018 | 6
MODU | NG Rig 3 | Bonga 740 SE w3 | COM - LOWER COMPLETION | BMPh2b-740 SE w3 - Lower Completion | 2018-01-19 | 2018-01-26 | 2018 | 2018 | 7
MODU | NG Rig 3 | Bonga 740 SE w3 | COM - UPPER COMPLETION | BMPh2b-740 SE w3 - Upper Completion | 2018-01-26 | 2018-02-05 | 2018 | 2018 | 10
MODU | NG Rig 3 | NG Rig 3 DEMOB | RIG - DEMOBILISATION | Demobilisation of the rig | 2018-02-05 | 2018-02-15 | 2018 | 2018 | 10
MODU | Noble Globetrotter 2 | SILE-1 | DRL - DRILL AND ABANDON | Drill and Abandon - Turkey | 2015-02-17 | 2015-05-29 | 2015 | 2015 | 101
MODU | Noble Globetrotter 2 | LEOPARD MARIN 2 | RIG MOVE/PREP | Move rig to Gabon | 2015-05-29 | 2015-06-17 | 2015 | 2015 | 19
MODU | Noble Globetrotter 2 | LEOPARD MARIN 2 | DRL - DRILL AND ABANDON | Leopard Appraisal (incl. Core & Logging) | 2015-06-17 | 2015-09-17 | 2015 | 2015 | 92
MODU | Noble Globetrotter 2 | LEOPARD MARIN 2 | WELL TEST | Well test | 2015-09-17 | 2015-11-02 | 2015 | 2015 | 46
DVA | Picaroon | PICAROON B4 | ABANDONMENT |  | 2014-11-27 | 2014-12-23 | 2014 | 2014 | 26
DVA | Picaroon | PICAROON B2 | ABANDONMENT |  | 2014-12-23 | 2015-02-14 12:00 | 2014 | 2015 | 53.5
DVA | Picaroon | PICAROON B3 | ABANDONMENT |  | 2015-02-14 | 2015-03-15 | 2015 | 2015 | 29
DVA | Picaroon | PICAROON B6 | ABANDONMENT |  | 2015-03-15 | 2015-04-28 | 2015 | 2015 | 44
DVA | Picaroon | PICAROON B1 | ABANDONMENT |  | 2015-04-28 | 2015-05-12 | 2015 | 2015 | 14
DVA | Cougar | COUGAR A1 | ABANDONMENT |  | 2014-12-03 | 2015-03-14 | 2014 | 2015 | 101
DVA | Cougar | COUGAR A4 | ABANDONMENT |  | 2015-03-14 | 2015-05-01 | 2015 | 2015 | 48
DVA | Cougar | COUGAR A8 | ABANDONMENT |  | 2015-05-01 | 2015-07-06 | 2015 | 2015 | 66
DVA | Cougar | COUGAR A28 | ABANDONMENT |  | 2015-07-06 | 2015-09-10 | 2015 | 2015 | 66
DVA | Cougar | COUGAR A6 | ABANDONMENT |  | 2015-09-10 | 2015-11-15 | 2015 | 2015 | 66
DVA | Cougar | COUGAR A17 | ABANDONMENT |  | 2015-11-15 | 2016-02-03 | 2015 | 2016 | 80
DVA | Cougar | COUGAR A16 | ABANDONMENT |  | 2016-02-03 | 2016-04-23 | 2016 | 2016 | 80
DVA | Cougar | COUGAR 20 | ABANDONMENT |  | 2016-04-23 | 2016-07-12 | 2016 | 2016 | 80
DVA | Cougar | COUGAR A14 | ABANDONMENT |  | 2016-07-12 | 2016-09-30 | 2016 | 2016 | 80
DVA | Cougar | COUGAR A18 | ABANDONMENT |  | 2016-09-30 | 2016-12-19 | 2016 | 2016 | 80
DVA | Cougar | COUGAR A21 | ABANDONMENT |  | 2016-12-19 | 2016-12-30 | 2016 | 2016 | 11
DVA | Cougar | COUGAR A22 | ABANDONMENT |  | 2016-12-30 | 2017-01-10 | 2016 | 2017 | 11
DVA | Cougar | COUGAR A23 | ABANDONMENT |  | 2017-01-10 | 2017-01-21 | 2017 | 2017 | 11
DVA | Cougar | COUGAR 24 | ABANDONMENT |  | 2017-01-21 | 2017-02-01 | 2017 | 2017 | 11
DVA | Cougar | COUGAR A7 | ABANDONMENT |  | 2017-02-01 | 2017-02-12 | 2017 | 2017 | 11
DVA | Cougar | COUGAR A31 | ABANDONMENT |  | 2017-02-12 | 2017-02-23 | 2017 | 2017 | 11
DVA | Cougar | COUGAR A25 | ABANDONMENT |  | 2017-02-23 | 2017-03-06 | 2017 | 2017 | 11
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]